## Project Info
PROJECT INFO
The single source of truth for project identity. Dashboard, every log's header, and every Skill-drafted document pull from here — fill it in once per project.
Project Name | Norcross, GA
Project Number | #1517
Job Number | 15170000GR
Project Address | 4990 Jimmy Carter Blvd, Norcross, GA 30093
AHJ / Jurisdiction | Gwinnett County, GA; Norcross, GA
Owner | Lidl US Operations, LLC
Owner Contact (name / email / phone) | Jens Byer / jens.byer@lidl.us / 571-867-0856
Architect / Design Firm | Progressive Companies
Architect Contact
General Contractor | Place Services, Inc
GC Project Manager | Bobby McTeague
GC Superintendent | Tim Mauldin
Contract Type / Delivery Method | Lump Sum
Contract Date
Notice to Proceed Date | 2026-09-25
Substantial Completion Date (Contract) | 2027-06-21
Original Contract Value ($) | 7958879
Approved Change Orders to Date ($) | 0
Current Contract Value ($) | 7958879
Prepared By | Luis Marcelino
Preparer Company | Place Services, Inc
Last Updated | 2026-10-01
Cells shaded light gray are for manual entry. Approved Change Orders, Current Contract Value, and Last Updated are live formulas — don't type over them.

## README
PROJECT CONTROL TRACKER — HOW THIS WORKBOOK WORKS
This is the shared tracker the Claude Skills in this pack read from and write to.
TABS:
Project Info Project identity — name, number, owner, contract dates, team, the
preparer. Fill this in ONCE per project; everything else reads from it.
Dashboard Live counts and totals pulled from every log below.
RFI Log One row per RFI. Status/Days Open/Overdue calculate automatically;
Void? flags a voided RFI, Revision # tracks reissues.
Submittal Log One row per submittal package.
Change Order Log GC -> OWNER: PCO through to executed CO, linked back to RFIs/Claims.
Trade(s) tags which trade(s) the cost/backup applies to.
Subcontractor CO Log SUB -> GC: change orders a subcontractor submitted for your review,
tracked against their Subcontract # and a running approved total per sub.
Separate from the Change Order Log above — do not merge the two.
Claims Log Tracks notice deadlines (defaults to AIA A201 21-day window — verify
against YOUR executed contract).
Risk Register Probability x Impact scoring, auto priority.
Daily Log One row per working day.
Meeting Minutes Log One row per action item (a meeting = several rows).
Contract Review Log Clause-by-clause deviation tracking vs. your standard playbook.
Contract Milestones Owner-contract dates (NTP, Substantial/Final Completion, etc.) with
auto status: On Track / Due Soon / Missed / Met - On Time / Met - Late.
Schedule INTERNAL USE ONLY — activity-level baseline vs. forecast tracking.
Not pulled into the Owner Report; kept here for your own PM use.
3-Week Look-Ahead A WEEKLY FEED you provide — paste/replace it each week. The Owner
Report pulls it in as given; Claude doesn't generate or recalculate it.
Photo Log Index of jobsite photos (image files live alongside this workbook;
this tab just references them by name).
Permit Tracker Every trade/permit needed, status through Applied/Under Review/In
Hand, with an auto Flag (ACTION NEEDED / EXPIRING SOON). Use the
Permit Skill to research what's actually required for your AHJ.
Material Tracker Procurement log — one row per material/equipment order, status
Not Ordered through Received, auto-flags OVERDUE deliveries, and
carries Lead Time and Vendor Contact for the buyout/responsibility
matrix.
Drawing Log One row per sheet, a column per tracked revision (Bid -> Addenda ->
Revisions -> Award). Use the Drawing Management Skill for a full
sheet-by-sheet comparison between two revisions.
Specification Log One row per spec section. Set Spec Format / Edition once at the top
(MasterFormat 1995 vs. 2004+ vs. UniFormat, etc. — the Specification
Management Skill detects which one your spec book actually uses). Use it
Management Skill to generate the Submittal Register straight from it.
Owner Contract Key Retainage, payment terms, notice deadlines, closeout requirements,
Terms and more, extracted from the actual executed contract by the Owner
Contract Skill. NOT AIA-only — works from GMP, Design-Build, IPD,
ConsensusDocs, EJCDC, or custom Lump Sum contracts too. Placeholder
values shown are common reference points, not your contract's actual
terms — CONFIRM every field against your executed contract.
BACKUP DOCUMENTS:
RFI Log, Submittal Log, Change Order Log, Claims Log, Meeting Minutes Log, Contract
Review Log, Permit Tracker, and Material Tracker each have a 'Backup Documents' column
(file names, semicolon-separated) and most also have a 'Backup Required?' flag. Keep the
actual files in the same folder/Drive as this workbook. When a Skill drafts or logs an
item, it will list backup documents as available, note when they're contractually
required (cost backup on a CO, the permit itself once issued, cut sheets on a submittal,
etc.), and flag it plainly if something required is missing rather than leaving it blank.
RUNNING MORE THAN ONE PROJECT:
One workbook = one project. Don't add a second project's rows into this file — copy this
template and make a new workbook instead. Name each file so it's unambiguous at a glance:
<Project Number>_<Project Name>_Project_Control_Tracker.xlsx
e.g. 3382_SpinJoy_Project_Control_Tracker.xlsx
Fill in the Project Info tab first in every new copy — it's what Claude reads to confirm
which project it's working on, and what every Skill puts in a drafted document's header.
If you paste several tracker files into one conversation or Project, or several projects'
files just live in the same folder Claude can see, always say which project a request is
for by name or number ('for 3382 SpinJoy, draft an RFI about...') — Claude should ask which
workbook to use if it's genuinely ambiguous rather than guessing, and should never merge
or cross-reference rows from two different projects' trackers into one document.
HOW THE LOGS LINK TOGETHER:
- RFI Log 'Linked CO #' <-> Change Order Log 'Linked RFI #'
- Change Order Log 'Linked Claim #' <-> Claims Log 'Linked CO #'
- Risk Register 'Linked CO #' / 'Linked Claim #' point back to those logs
- Daily Log 'Linked RFI #(s)' / 'Linked Submittal #(s)' / 'Photo Ref #(s)' point forward
- Meeting Minutes 'Linked RFI/CO/Risk #' ties action items to the source item
- Photo Log 'Linked Daily Log Date' / 'Linked RFI/CO/Risk #' ties photos back to events
These are reference columns, not live formulas (item numbers are typed once, reused
everywhere) — this keeps the sheet fast and lets Claude cite exact numbers when it drafts.
HOW TO USE WITH CLAUDE:
0. Fill in the Project Info tab first — Claude reads it to confirm which project it's
working on and to fill in headers (project name, number, owner, etc.) automatically
rather than asking you for them on every request.
1. Keep this workbook as your single source of truth (in Claude Project files, Google
Drive, or wherever your Skill's instructions point). Keep photo image files in the
same folder, named to match the Photo Log.
2. Load the matching Skill (e.g., 'RFI Skill') and ask Claude to draft a document.
3. Claude drafts the letter/notice/report AND gives you the exact new row to paste into
the matching log tab — so the tracker and the document never fall out of sync.
4. Re-upload the updated workbook next session (or keep it in a Project) so Claude's
status counts, notice-deadline checks, and cross-references stay accurate.
5. For the Weekly Owner Report specifically, use the Owner Report Skill — it pulls the FULL
status of every RFI, Submittal, Change Order/PCO, Permit, and Material/procurement item
(not just the problem ones), Contract Milestones (if the tab has rows), Risk Register,
Daily Log delays, the 3-Week Look-Ahead feed you provide, and Photo Log, into a
formatted Word document. The internal Schedule tab is deliberately NOT part of that
report.
6. For permits specifically, use the Permit Skill — it can research what permits a given
scope of work typically needs in your jurisdiction (always confirm with the AHJ
directly) and keeps the Permit Tracker in sync. For procurement, use the Material
Tracker Skill to log new orders and check status/overdue deliveries.
7. RFI, Submittal, Change Order, Claims, and Risk each generate a standalone Excel report
(all rows, regardless of status) on request — 'give me today's RFI report' / 'this
week's change order report'. These are separate files from the tracker itself, meant
to hand off to a distribution list.
8. For subcontractor-submitted change orders, use the Subcontractor CO Skill — it reviews
what a sub submitted against their subcontract, the drawings, and the specs before you
set a status, and keeps the Subcontractor CO Log in sync.
9. For the Owner Contract itself — summaries, redline review, milestone/retainage/payment
extraction, weekly deadline reminders — use the Owner Contract Skill. It populates the
Owner Contract Key Terms tab from your ACTUAL contract, not from AIA assumptions.
10. For subcontract scopes of work and reviewing a sub's redlines against Owner-contract
flow-down requirements, use the Subcontractor Contract Skill.
11. For drawing tracking and revision comparisons, use the Drawing Management Skill — it
keeps the Drawing Log in sync and can do a detailed sheet-by-sheet comparison between
two revisions when both are available.
12. For specifications — logging, the submittal register, closeout/procurement
requirements — use the Specification Management Skill.
13. For geotech reports, Phase I/II ESAs, and similar supporting documents, use the Other
Contract Documents Skill — it turns findings into Risk Register entries, subcontractor
awareness notes, and specific bid/subcontract exclusion language.
Cells shaded light gray are for manual entry. Everything else is a live formula — don't
type over white/formula cells or you'll break the calculation for that column.
Delete the example (row 2) on every log tab before starting real project data.

## Dashboard
PROJECT CONTROL DASHBOARD
Auto-calculated from every log below. Project identity is set once, on the Project Info tab.
Project Name: | Norcross, GA
Project Number: | #1517
Report Date: | 2026-10-01
RFIs
Open | 0
Overdue | 0
Closed | 6
Submittals
Pending / in review | 8
Revise & Resubmit | 0
Change Orders
Pending | 2
Approved value ($) | 0
Subcontractor Change Orders
Under review | 0
Rejected | 0
Approved value ($) | 56430
Claims
Open | 0
Late notice (non-compliant) | 0
Risk Register
High priority, open | 0
Total open risks | 0
Action Items (Meeting Minutes)
Open | 12
Overdue | 0
Contract Review
High-risk deviations, open | 0
Contract Milestones
Missed | 0
Met late | 0
Due soon (14 days) | 0
Permits
Action needed | 0
Expiring soon (30 days) | 0
Issued / in hand | 0
Procurement / Materials
Not ordered | 0
Overdue deliveries | 0
Received | 0
Schedule (internal use — not in Owner Report)
Activities delayed | 0
Activities at risk | 0
Stale Items (no activity in 14+ days)
RFIs | 0
Submittals | 5
Change Orders | 2
Subcontractor Change Orders | 0
Claims | 0
Risks | 0
Permits | 0
Materials | 0

## RFI Log
RFI # | Date Submitted | Submitted By | Subject | Spec Section / Drawing Ref | Question | Assigned To | Response Due Date | Response | Date Answered | Status | Days Open | Cost Impact ($) | Schedule Impact (days) | Linked CO # | Linked Submittal # | Backup Documents | Backup Required? | Revision # | Void? | Last Activity Date | Days Since Activity
RFI-001 | 2026-04-07 | Luis Marcelino, Place Services Inc. | Civil CAD File - Waiver & CAD Release (Lidl portal RFI #58) | Civil plan set (CHA Project No. 20-LD-073); no sheet/spec # listed | Can you provide the Waiver and CAD for the Civil plan for the Site Contractor to start working on his import? | Christopher Manes, CHA Consulting, Inc. | 2026-04-10 | Sign the attached AutoCAD data release letter (dated 04/17/26) and return to C. Manes (CHA); CAD file to be provided upon receipt of signed letter. Portal status: Closed 08/26/26. | 2026-04-17 | Closed | 10 | 0 | 0 |  |  | AutoCAD data release letter_04.17.26.pdf (included in RFI portal export) | No | 0 | No | 2026-04-17
RFI-002 | 2026-04-07 | Luis Marcelino, Place Services Inc. | Storm Structures - New vs. Existing (Lidl portal RFI #59) | Civil storm drainage: STR15X, STR16X, STR17, STR18X (STR19X added in response); no sheet # listed | Confirm STR15X (Junction Box), STR16X (Junction Box) and STR18X (Double Wing Catch Basin), and whether STR17 (not labeled "X" but has an existing pipe connected) is an existing structure to remain, to define scope without gaps/overlaps with suppliers. | Jeff Belyea, CHA Consulting, Inc. | 2026-04-10 | Storm structures 15x, 16x, 17, and 19x are new structures to be set on the existing storm system. Storm structure 18x is an existing structure to remain. (J. Belyea, 04/08/26) | 2026-04-08 | Closed | 1 | 0 | 0 |  |  |  | No | 0 | No | 2026-04-10
RFI-003 | 2026-04-15 | Luis Marcelino, Place Services Inc. | Storefront System - Kawneer vs. Schaal (Lidl portal RFI #60) | Storefront system (BOD Kawneer; Schaal national account); no sheet/spec # listed | BOD is Kawneer but Schaal is National Account. Are we able to use the Kawneer system? | Progressive Companies - Shelley Chovan (also Gabriela Camarillo, Jenna Giha, Stacey Vroman) | 2026-04-20 | Schaal must be used. (S. Chovan, 04/20/26) | 2026-04-20 | Closed | 5 | 0 | 0 |  |  |  | No | 0 | No | 2026-04-20
RFI-004 | 2026-08-26 | Luis Marcelino, Place Services Inc. | Arch + MEP CAD Release (Lidl portal RFI #61) | Architectural and MEP drawings; no sheet # listed | Can you please provide CAD for the Arch and MEPs? | Progressive Companies - Amy Schoch (also Alex Hengstebeck, Gabriela Camarillo, Jenna Giha, Shelley Chovan, Stacey Vroman) | 2026-08-31 | CAD Release with PSI has been completed and CAD files were sent on 9/2/26. If the GC needs additional CAD files, send via email to the Progressive team and NOT an RFI. (A. Schoch, 09/08/26) | 2026-09-08 | Closed | 13 | 0 | 0 |  |  | Lidl Norcross GA - RFI 61 - Arch and MEP CAD Release_PC Response.pdf (included in RFI portal export) | No | 0 | No | 2026-09-08
RFI-005 | 2026-08-31 | Luis Marcelino, Place Services Inc. | HVAC - BMS Integration (Airius Destratification Fans) & Fire/Smoke Dampers (Lidl portal RFI #62) | HVAC / destratification fan schedule; mechanical drawings (no sheet # listed) | 1. Airius Destratification Fans: Airius advises BMS integration is not available with the basis-of-design model number - please advise. 2. Fire/Smoke Dampers: none shown on the drawings - are we to exclude? | Progressive Companies - Amy Schoch (also Alex Hengstebeck, Gabriela Camarillo, Jenna Giha, Shelley Chovan, Stacey Vroman) | 2026-09-03 | 1. Provide destratification fans as called out in the schedule; fans to be set up for operation independent of BMS. 2. No fire/smoke dampers required; ducts are not penetrating any fire rated partitions. (J. Martinez Sabag, Mech. Eng. Designer, 09/11/26) | 2026-09-11 | Closed | 11 | 0 | 0 |  |  | Lidl Norcross GA - RFI 62 - HVAC - BMS Integration and Dampers_PC Response.pdf (included in RFI portal export) | No | 0 | No | 2026-09-11
RFI-006 | 2026-09-18 | Tucker Teague, Place Services Inc. | Signal Plans Not Included in Authorized Plan Set (Lidl portal RFI #63) | Traffic signal plans; Authorized plan set AUTHORIZED-EPN2024-00519 (Gwinnett County) | Traffic Improvements Sub submitted signal plans to Gwinnett County; E. Diamond (County Traffic Mgmt Systems Engineer) advised they are not in the authorized plan set and has requested CHA coordinate directly with the County to resolve. Please have the appropriate CHA representative contact E. Diamond and provide required information/revised documentation. | CHA Consulting, Inc. - Christopher Manes (also JaWanna English-Neal, Jeff Belyea, Todd Seldomridge) | 2026-09-23 | Final stamped plans from the County Traffic team were included in the Authorized plan set approved by Planning and Development. Authorized plans attached for reference; these are the documents to be used for construction. (C. Manes, 09/23/26; portal status Closed 09/28/26) | 2026-09-23 | Closed | 5 | 0 | 0 |  |  | #1517 Lidl Norcross, GA - Traffic Management Systems Engineer Contact Information.png; #1517 Lidl Norcross, GA - RFI - Signal Plans Not Included in Authorized Plan Set.pdf; AUTHORIZED-EPN2024-00519.pdf (response) | Yes | 0 | No | 2026-09-23
Legend: gray-filled columns are for manual entry. Status, Days Open auto-calculate — Status reads Void? first, then Closed/Overdue/Open. Revision # increments each time an RFI is reissued/revised (0 = original). Last Activity Date is the most recent of Date Submitted/Response Due/Date Answered; Days Since Activity flags in red at 14+ days on anything not Closed — this is what feeds the Dashboard's Stale Items section. Row 2 is an example — delete before use.
Formulas:
Status = IF([RFI #]="","",IF([Void?]="Yes","Void",IF([Response]<>"","Closed",IF(AND([Response Due Date]<>"",TODAY()>[Response Due Date]),"Overdue","Open"))))
Days Open = IF([RFI #]="","",IF([Response]<>"",[Date Answered]-[Date Submitted],TODAY()-[Date Submitted]))
Last Activity Date = IF([RFI #]="","",MAX([Date Submitted]+0,[Response Due Date]+0,[Date Answered]+0))
Days Since Activity = IF([RFI #]="","",IF([Status]="Closed","",TODAY()-[Last Activity Date]))

## Submittal Log
Submittal # | Spec Section | Description | Type | Subcontractor | Date Rec'd from Sub | Date Sent to Architect | Required Return Date | Date Returned | Status | Days in Review | Linked RFI # | Backup Documents | Backup Required? | Last Activity Date | Days Since Activity
SUB-001 | 23 0503 | HVAC Package Rev 0 (Procore 230503-1.0 / Fieldwire PSI-0004) - Lennox RTUs & mini-split, CaptiveAire, ductwork, Greenheck/Titus & Fantech/Airius air distribution, prelim TAB. Reviewer: Make Corrections Noted 9/14 - provide missing EF-1 & air terminal info (addressed in Rev 1). Req'd return = 14-day default; Procore had no due date. | Product Data | Platinum Air Systems | 2026-09-03 | 2026-09-09 | 2026-09-23 | 2026-09-24 | Approved as Noted | 15 |  | SUB-001_R1_Original_Procore_Export_2026-10-01.pdf; Submittal-001_Transmittal_Packaged.pdf (package INCLUDED, 659 pp); SUB-001_R0_Reviewed_MakeCorrectionsNoted_2026-09-14.pdf; SUB-001_R1_Reviewed_MakeCorrectionsNoted_2026-09-28.pdf; SUB-001_R1_As-Submitted_PSI-0004_2026-09-22.pdf - folder: documents\submittals\SUB-001 - 230503 HVAC | Yes | 2026-09-24
SUB-001-R1 | 23 0503 | HVAC Package Rev 1 (Procore 230503-1.1) - corrections made; EF-1 (SE1-10-440-VG) & Titus air terminals added. Reviewer: Make Corrections Noted 9/28 - OPEN: provide TG-1 per plans and diffuser/register/grille schedule. Procore still Open, ball in court Amy Schoch (Progressive). | Product Data | Platinum Air Systems | 2026-09-22 | 2026-09-22 | 2026-10-14 | 2026-09-28 | Approved as Noted | 6 |  | SUB-001_R1_Original_Procore_Export_2026-10-01.pdf; Submittal-001_Transmittal_Packaged.pdf (package INCLUDED, 659 pp); SUB-001_R0_Reviewed_MakeCorrectionsNoted_2026-09-14.pdf; SUB-001_R1_Reviewed_MakeCorrectionsNoted_2026-09-28.pdf; SUB-001_R1_As-Submitted_PSI-0004_2026-09-22.pdf - folder: documents\submittals\SUB-001 - 230503 HVAC | Yes | 2026-10-14
SUB-002 | 33 4100 | Stormwater Package Rev 0 (Procore 33 4100-2.0 / Fieldwire PSI-0002) - Hydro International First Defense hydrodynamic separator (ST8), Up-Flo water quality filter (ST5), Southeast Culvert 84in CMP underground detention. Reviewer: CHA Consulting (Christopher Manes) - no response. Req'd return per Fieldwire response due 9/9; Procore has no due date. | Product Data | Coles Construction | 2026-08-26 | 2026-08-26 | 2026-09-09 |  | Pending | 36 |  | SUB-002_R0_Original_Procore_Export_2026-10-01.pdf; Submittal-002_Transmittal_Packaged.pdf (package INCLUDED, 62 pp) - folder: documents\submittals\SUB-002 - 334100 Storm Drainage | Yes | 2026-09-09 | 22
SUB-003 | 33 4100 | HDPE Pipe Rev 0 (Procore 33 4100-1.0, Package #1 Site Utilities / Fieldwire PSI-0001) - ADS N-12 ST IB storm pipe (pkg Section 1). Attachment is the full Core & Main site utility package; Procore splits Package #1 into one item per spec section (sanitary = SUB-004). Reviewer: CHA Consulting (Christopher Manes) - no response. Req'd return per Fieldwire response due 9/11; Procore has no due date. | Product Data | Coles Construction (supplier Core & Main) | 2026-08-26 | 2026-08-26 | 2026-09-11 |  | Pending | 36 |  | SUB-003_R0_Original_Procore_Export_2026-10-01.pdf; Submittal-003_Transmittal_Packaged.pdf (package INCLUDED, 92 pp) - folder: documents\submittals\SUB-003 - 334100 Site Utilities | Yes | 2026-09-11 | 20
SUB-004 | 33 3000 | Sanitary Sewer Rev 0 (Procore 33 3000-1.0, Package #1 Site Utilities / Fieldwire PSI-0001) - Diamond Sani-21 PVC sewer pipe & fittings, cleanouts, Star Pipe heavy-duty covers, marking tape (pkg Section 2, export pp. 8-19). Same PSI-0001 attachment as SUB-003. Reviewer: CHA Consulting (Christopher Manes) - no response. Req'd return per Fieldwire response due 9/11; Procore has no due date. | Product Data | Coles Construction (supplier Core & Main) | 2026-08-26 | 2026-08-26 | 2026-09-11 |  | Pending | 36 |  | SUB-004_R0_Original_Procore_Export_2026-10-01.pdf; SUB-004_R0_Sanitary_Section_Only.pdf; Submittal-004_Transmittal_Packaged.pdf (package INCLUDED, 92 pp) - folder: documents\submittals\SUB-004 - 333000 Sanitary Sewer | Yes | 2026-09-11 | 20
SUB-005 | 33 1000 | Domestic Water & Irrigation Rev 0 (Procore 33 1000-1.0, Package #1 Site Utilities / Fieldwire PSI-0001) - PVC pressure pipe & DI fittings, 2in tap assemblies (Smith-Blair 313, Ford Meter Box), 2in DCV (Wilkins 950XLT), irrigation, 2in RPZ (Wilkins 975XL2) (pkg Section 3, export pp. 20-53). Same PSI-0001 attachment as SUB-003/004. Reviewer: CHA Consulting (Christopher Manes) - no response. Req'd return per Fieldwire response due 9/11; Procore has no due date. | Product Data | Coles Construction (supplier Core & Main) | 2026-08-26 | 2026-08-26 | 2026-09-11 |  | Pending | 36 |  | SUB-005_R0_Original_Procore_Export_2026-10-01.pdf; SUB-005_R0_Domestic_Water_Section_Only.pdf; Submittal-005_Transmittal_Packaged.pdf (package INCLUDED, 92 pp) - folder: documents\submittals\SUB-005 - 331000 Domestic Water | Yes | 2026-09-11 | 20
SUB-006 | 33 | Fire Main Rev 0 (Procore 33-1.0, Package #1 Site Utilities) - U.S. Pipe Tyton DI pipe & fittings, tapping sleeve, M&H 129 hydrant, 8in DCDA BFP vault (Wilkins 350ASTDA), 8in PIV, 8in gate valve (PSI-0001 pkg Section 4, export pp. 54-91). FLAG: Procore item has NO ATTACHMENT (cover only) and spec is division-level '33 - Utilities' - confirm CHA has the fire main cut sheets. Reviewer: CHA Consulting (Christopher Manes) - no response. Req'd return per Fieldwire response due 9/11. | Product Data | Coles Construction (supplier Core & Main) | 2026-08-26 | 2026-08-26 | 2026-09-11 |  | Pending | 36 |  | SUB-006_R0_Procore_Cover_Only_2026-10-01.pdf (Procore item has NO attachment); SUB-006_R0_Fire_Main_Section_REFERENCE_from_PSI-0001.pdf (from SUB-003 copy); Submittal-006_Transmittal_Packaged.pdf (42 pp) - folder: documents\submittals\SUB-006 - 33 Fire Main | Yes | 2026-09-11 | 20
SUB-007 | 22 (22 1119) | Plumbing Package Rev 0 (Procore 22-1.0, Package #2 Plumbing / Fieldwire PSI-0003) - fixtures (DF, L, WC, SK-1/2/3), hydrants, floor drains/sinks, PRV, EWH-1, gas meter. Procore CLOSED. Reviewer (Progressive, bizons 9/25): Make Corrections Noted - OPEN: SK-3 replace Elkay SS8354LR4 with Elkay 14-3C16X20-L-18X per CCD 01 (05/28/2026). Returned 14 days after 9/11 due date. | Product Data | Golden Hands Plumbing (supplier Cowan Supply) | 2026-08-26 | 2026-09-03 | 2026-09-11 | 2026-09-25 | Approved as Noted | 22 |  | SUB-007_R0_Original_Procore_Export_2026-10-01.pdf; SUB-007_R0_Reviewed_MakeCorrectionsNoted_2026-09-25.pdf; SUB-007_R0_As-Submitted_PSI-0003_2026-09-03.pdf; Submittal-007_Transmittal_Packaged.pdf (package INCLUDED, 217 pp) - folder: documents\submittals\SUB-007 - 22 Plumbing | Yes | 2026-09-25
SUB-008 | None (Procore '1 - Default') | CCTV Submittal Rev 0 (Procore 1-3.0 / Fieldwire PSI-0007) - off-site traffic signal Gwinnett Co. TS-082, Jimmy Carter Blvd @ Shelby Dr: AXIS Q6086-E PTZ camera, Major Custom Cable CAT6 100ft, DITEK DTK-MRJPOES surge protector, AXIS TQ5001-E mount (Utilicom quote 62085). No spec section assigned. Reviewer: CHA Consulting (Christopher Manes) - no response; confirm whether Gwinnett DOT review also required. Req'd return per Fieldwire response due 9/25. | Product Data | R.J. Haynie & Associates (supplier Utilicom Supply Associates) | 2026-08-31 | 2026-09-18 | 2026-09-25 |  | Pending | 13 |  | SUB-008_R0_Original_Procore_Export_2026-10-01.pdf; Submittal-008_Transmittal_Packaged.pdf (package INCLUDED, 18 pp) - folder: documents\submittals\SUB-008 - CCTV Traffic Signal | Yes | 2026-09-25 | 6
SUB-009 | None (Procore '1 - Default') | Mast Arm Pole Shop Drawings #1-#3 Rev 0 (Procore 1-2.0 / Fieldwire PSI-0006) - off-site traffic signal Gwinnett Co. TS-082, Jimmy Carter Blvd @ Shelby Dr: Valmont GA672263P1 (2 sheets, GA PE sealed 8/31) Poles B (22ft, 65+55ft arms) & C (30ft, 55+55ft arms) + orientation sketch. FLAG: foundation callout (3ft dia x 14.5ft, (8) #10) is an unsigned annotation, not on sealed dwg - verify. Reviewer: CHA Consulting (Christopher Manes) - no response; confirm Gwinnett DOT review. Req'd return per Fieldwire due 9/25. | Shop Drawing | R.J. Haynie & Associates (Valmont via DOT Lighting / Traffic & Lighting Corp) | 2026-08-31 | 2026-09-18 | 2026-09-25 |  | Pending | 13 |  | SUB-009_R0_Original_Procore_Export_2026-10-01.pdf; Submittal-009_Transmittal_Packaged.pdf (package INCLUDED, 6 pp) - folder: documents\submittals\SUB-009 - Mast Arm Poles | Yes | 2026-09-25 | 6
SUB-010 | None (Procore '1 - Default') | Mast Arm Pole Submittals Rev 0 (Procore 1-1.0 / Fieldwire PSI-0005) - Valmont structural calcs, Order 672263-P1 (94 pp), Poles B (P22 M65/M55) & C (P30 M55/M55), AASHTO 2015, 115 mph - off-site signal Gwinnett Co. TS-082. Related to SUB-009 shop dwgs. FLAG: calcs give foundation reactions only, no foundation design; PE seal is image stamp, not digitally signed. Reviewer: CHA Consulting (Christopher Manes) - no response. Req'd return per Fieldwire due 9/25. | Product Data | R.J. Haynie & Associates (Valmont Industries) | 2026-08-31 | 2026-09-18 | 2026-09-25 |  | Pending | 13 |  | SUB-010_R0_Original_Procore_Export_2026-10-01.pdf; Submittal-010_Transmittal_Packaged.pdf (package INCLUDED, 99 pp) - folder: documents\submittals\SUB-010 - Mast Arm Pole Calcs | Yes | 2026-09-25 | 6
Legend: gray-filled columns are for manual entry. Days in Review auto-calculates. Last Activity Date / Days Since Activity feed the Dashboard's Stale Items section. Row 2 is an example — delete before use.
Formulas:
Days in Review = IF([Submittal #]="","",IF([Date Returned]<>"",[Date Returned]-[Date Sent to Architect],IF([Date Sent to Architect]<>"",TODAY()-[Date Sent to Architect],"")))
Last Activity Date = IF([Submittal #]="","",MAX([Date Rec'd from Sub]+0,[Date Sent to Architect]+0,[Required Return Date]+0,[Date Returned]+0))
Days Since Activity = IF([Submittal #]="","",IF(OR([Status]="Approved",[Status]="Approved as Noted"),"",TODAY()-[Last Activity Date]))

## Change Order Log
PCO/CO # | Date Initiated | Description | Source | Trade(s) | Linked RFI # | Linked Claim # | Cost Amount ($) | Schedule Impact (days) | Status | Date Submitted to Owner | Date Approved (Owner CO) | Running Approved Total ($) | Backup Documents | Backup Required? | Last Activity Date | Days Since Activity | Bundled Into OCO #
PCO-001 | 2026-08-20 | Base bid material/fuel price escalation true-up (Q1 2026 bid to July 2026 award); 5% OH&P | Owner Request | Earthwork/Site Utilities, Roofing, Low Voltage, Metal Panels, Plumbing, Rooftop Screens, Doors/Frames/Hardware |  |  | 99986.52 | 0 | Pending |  |  | 0 | CO #01 - OCO Package - Pricing Escalation Rebalance.pdf (incl. PSI PCO-001 cost breakdown); 22_GC_CO_Template - CO01 rev1.xlsx; OCO #01 - Email Backup (7/29-8/3/2026) | Yes | 2026-08-20 | 42 | OCO-01
PCO-002 | 2026-08-25 | Allowance #01 - building demolition + ACM abatement; $224,903.34 drawn from $225,000 Demolition Allowance ($96.66 remaining); net $0 to Contract Sum; 9.8% GC OH&P | Owner Request | Demolition (Building & Site), Asbestos Abatement |  |  | 0 | 0 | Pending |  |  | 0 | CO #02 - OCO Package - Building Demolition & Abatement.pdf; Lidl 1517 Demolition Scope.pdf (Cole's demo proposal $148,400); SCO - Coles Construction CO-02.xlsx; Lidl #1517 - Change Order #2 - Asbestos Abatement.pdf (Cole's CO-02 / SCO-LOG-001); 22_GC_CO_Template - CO02.xlsx | Yes | 2026-08-25 | 37 | OCO-02
Running Approved Total sums col H where Status=Approved, in row order. Trade(s) tags which trade(s) the backup documents/cost breakdown apply to (comma-separated) — lets the weekly report and backup review group costs by trade. Last Activity Date / Days Since Activity feed the Dashboard's Stale Items section (blank once Approved/Rejected/Void). Bundled Into OCO # — a single Owner Change Order can combine multiple PCO rows (this is normal practice, e.g. bundling several CCDs into one OCO); tag every PCO row included in a given OCO with that OCO's number once it's issued for signature — use the Change Order Skill to build the actual signature-ready document. Row 2 is an example — delete before use.
Formulas:
Last Activity Date = IF([PCO/CO #]="","",MAX([Date Initiated]+0,[Date Submitted to Owner]+0,[Date Approved (Owner CO)]+0))
Days Since Activity = IF([PCO/CO #]="","",IF(OR([Status]="Approved",[Status]="Rejected",[Status]="Void"),"",TODAY()-[Last Activity Date]))

## Subcontractor CO Log
SCO Log # | Date Submitted | Subcontractor Name | Subcontract # | Description | Amount Requested ($) | Schedule Impact Requested (days) | Related Owner PCO/CO # | Related RFI # | Validity Assessment | Status | Date Reviewed | Reviewed By | Approved Amount ($) | Running Approved Total — This Sub ($) | Backup Documents | Backup Required? | Last Activity Date | Days Since Activity
SCO-LOG-001 | 2026-08-23 | Cole's Construction | 7 | CO-02 Asbestos abatement (Georgia Environmental): Main Event Hall ACM floor mastic/carpet glue/carpet + ACM roofing mastic at 8 roof vents | 56430 | 0 | PCO-002 / OCO-02 |  | Valid change: Subcontract No. 7 (8/4/2026) Exhibit A covers selective/building demolition but no asbestos/ACM abatement, and PSI's bid (exclusion h) excludes asbestos abatement. ACM black floor mastic and roof penetration cement are confirmed in Owner's NOVA pre-demolition ACM survey (3/18/2021). Sub O&P 10% = prime contract 4.2 sub cap. Optional $5,500 debris line excluded (debris to be cleared before mobilization). Additional unsampled roof/mirror glue ACM to come as a separate SCO. Approved contingent on Lidl executing CO #02. | Approved | 2026-10-01 | Luis Marcelino, General Manager | 56430 | 56430 | Lidl #1517 - Change Order #2 - Asbestos Abatement.pdf; SCO - Coles Construction CO-02.xlsx | Yes | 2026-10-01
This log is GC review of costs a SUBCONTRACTOR submitted — separate from the Change Order Log above (which tracks the GC's own PCOs/COs to the Owner). Validity Assessment is where the review against the subcontract, drawings, and specs gets recorded before a status is set. Running Approved Total is per-subcontractor (tracks against their original Subcontract # value) — a formula, never type over column O. Row 2 is an example — delete before use.
Formulas:
Last Activity Date = IF([Subcontractor Name]="","",MAX([Date Submitted]+0,[Date Reviewed]+0))
Days Since Activity = IF([Subcontractor Name]="","",IF(OR([Status]="Approved",[Status]="Rejected",[Status]="Void"),"",TODAY()-[Last Activity Date]))

## Claims Log
Claim # | Date of Occurrence | Notice Date | Days to Notice | Contract Notice Deadline (days) | Notice Compliant? | Description | Cost Claimed ($) | Time Claimed (days) | Linked CO # | Status | Resolution | Backup Documents | Backup Required? | Last Activity Date | Days Since Activity
AIA A201-2017 §15.1.3: written notice of claim generally due within 21 days of the event. Confirm the actual deadline in your executed contract/exhibits before relying on this. Last Activity Date / Days Since Activity feed the Dashboard's Stale Items section. Row 2 is an example.

## Risk Register
Risk ID | Date Identified | Category | Description | Probability (1-5) | Impact (1-5) | Risk Score | Priority | Mitigation Plan | Owner | Linked CO # | Linked Claim # | Status | Last Updated | Days Since Update
Risk Score = Probability x Impact (1-5 scale each). Last Updated is MANUAL — update it yourself whenever you touch a risk (there's no second date field to compute this from automatically); Days Since Update feeds the Dashboard's Stale Items section. Row 2 is an example — delete before use.

## Daily Log
Date | Weather | Temp (F) | Crew Count | Subs on Site | Work Performed | Equipment on Site | Deliveries | Visitors | Safety Incidents | Delays / Issues | Linked RFI #(s) | Linked Submittal #(s) | Photo Ref #(s)
One row per working day. Row 2 is an example — delete before use.

## Meeting Minutes Log
Meeting # | Date | Type | Attendees | Key Discussion Point | Action Item | Responsible Party | Due Date | Status | Linked RFI/CO/Risk # | Backup Documents
OAC-001 | 2026-10-01 | OAC | Luis F. Marcelino (Place Services Inc.); Tucker Teague (Place Services Inc.); Jens Byer; Chris Manes (CHA Consulting, Inc.); Gabriela Camarillo (Progressive Companies) | Mobilization and demolition start - on site Mon 10/5/2026 | Confirm Monday 10/5 mobilization to Jens and Chris | Luis F. Marcelino | Before 10/5/2026 | Open |  | documents\meeting minutes\OAC\Meeting_Minutes_OAC-001_2026-10-01_Rev1.pdf
OAC-001 | 2026-10-01 | OAC | Luis F. Marcelino (Place Services Inc.); Tucker Teague (Place Services Inc.); Jens Byer; Chris Manes (CHA Consulting, Inc.); Gabriela Camarillo (Progressive Companies) | County pre-con meetings - traffic/ROW (R.J. Haynes) | Schedule county pre-con for traffic / right-of-way work | R.J. Haynes | Before any ROW work - DATE NEEDED | Open | RFI-006
OAC-001 | 2026-10-01 | OAC | Luis F. Marcelino (Place Services Inc.); Tucker Teague (Place Services Inc.); Jens Byer; Chris Manes (CHA Consulting, Inc.); Gabriela Camarillo (Progressive Companies) | County pre-con meetings - utility work (Cole's Construction, site contractor) | Schedule county pre-con for utility work | Cole's Construction | Before utility work - DATE NEEDED | Open
OAC-001 | 2026-10-01 | OAC | Luis F. Marcelino (Place Services Inc.); Tucker Teague (Place Services Inc.); Jens Byer; Chris Manes (CHA Consulting, Inc.); Gabriela Camarillo (Progressive Companies) | County pre-con meetings - correspondence distribution | Forward county correspondence to Jens and Chris | Luis F. Marcelino | Ongoing | Open
OAC-001 | 2026-10-01 | OAC | Luis F. Marcelino (Place Services Inc.); Tucker Teague (Place Services Inc.); Jens Byer; Chris Manes (CHA Consulting, Inc.); Gabriela Camarillo (Progressive Companies) | County inspector asked to meet team before work starts | Send inspector contact information to Luis | Chris Manes | TBD - DATE NEEDED | Open
OAC-001 | 2026-10-01 | OAC | Luis F. Marcelino (Place Services Inc.); Tucker Teague (Place Services Inc.); Jens Byer; Chris Manes (CHA Consulting, Inc.); Gabriela Camarillo (Progressive Companies) | County inspector asked to meet team before work starts | Contact inspector before starting work (including demo, if requested) | Luis F. Marcelino | Before 10/5/2026 | Open
OAC-001 | 2026-10-01 | OAC | Luis F. Marcelino (Place Services Inc.); Tucker Teague (Place Services Inc.); Jens Byer; Chris Manes (CHA Consulting, Inc.); Gabriela Camarillo (Progressive Companies) | Civil plan revisions resubmission on hold until Phase 1 E&S installed | Resubmit civil plan revisions; keep team informed of timing | Chris Manes | After Phase 1 E&S installed - DATE NEEDED | Open
OAC-001 | 2026-10-01 | OAC | Luis F. Marcelino (Place Services Inc.); Tucker Teague (Place Services Inc.); Jens Byer; Chris Manes (CHA Consulting, Inc.); Gabriela Camarillo (Progressive Companies) | Communication - copy Tucker Teague and Bobby McTeague on all emails | Add Tucker Teague and Bobby McTeague to all project correspondence | Jens Byer; Chris Manes | Immediately | Open
OAC-001 | 2026-10-01 | OAC | Luis F. Marcelino (Place Services Inc.); Tucker Teague (Place Services Inc.); Jens Byer; Chris Manes (CHA Consulting, Inc.); Gabriela Camarillo (Progressive Companies) | Recurring OAC meeting - Thursday afternoons | Send recurring Thursday-afternoon OAC invite to all attendees | Jens Byer | 2026-10-08 | Open
OAC-001 | 2026-10-01 | OAC | Luis F. Marcelino (Place Services Inc.); Tucker Teague (Place Services Inc.); Jens Byer; Chris Manes (CHA Consulting, Inc.); Gabriela Camarillo (Progressive Companies) | Site visit by Jens Byer within 2-3 weeks | Schedule site visit | Jens Byer | 10/22/2026 (approx.) | Open
OAC-001 | 2026-10-01 | OAC | Luis F. Marcelino (Place Services Inc.); Tucker Teague (Place Services Inc.); Jens Byer; Chris Manes (CHA Consulting, Inc.); Gabriela Camarillo (Progressive Companies) | Contract and Procore - executed contract upload | Upload fully executed contract to Procore | Jens Byer | TBD - DATE NEEDED | Open
OAC-001 | 2026-10-01 | OAC | Luis F. Marcelino (Place Services Inc.); Tucker Teague (Place Services Inc.); Jens Byer; Chris Manes (CHA Consulting, Inc.); Gabriela Camarillo (Progressive Companies) | Contract and Procore - inflation change item; demo/abatement against allowance | Log inflation discussion in Procore as a change item | Luis F. Marcelino | After contract upload - DATE NEEDED | Open | PCO pending (not yet in Change Order Log)
One row per discussion point / action item (a single meeting spans several rows). Row 2 is an example.

## Contract Review Log
Item # | Contract / Subcontract | Clause Ref | Standard Position (Playbook) | Actual Clause (Summary) | Deviation? | Risk Level | Recommended Redline | Status | Backup Documents
One row per clause reviewed against your standard playbook position. Row 2 is an example — delete before use.

## Schedule
Activity / Milestone | Baseline Start | Baseline Finish | Forecast Start | Forecast Finish | % Complete | Variance (days) | Status | Critical Path? | Responsible | Notes
Variance = Forecast Finish - Baseline Finish. Status: >5 days late = Delayed, 1-5 = At Risk, 0 or ahead = On Track. Row 2 is an example — delete before use.

## Contract Milestones
Milestone | Contract / Target Date | Actual / Forecast Date | Status | Responsible | Notes
Status: filled Actual/Forecast Date compares to Target (On Time / Late); no date yet compares Target to today (On Track / Due Soon within 14 days / Missed). These are the owner-contract dates (Substantial Completion, etc.) — distinct from the internal Schedule tab's activity-level forecasting. Rows 2-5 are examples — delete before use, and leave a milestone's row blank entirely if your contract doesn't set that date.

## 3-Week Look-Ahead
Week | Week Starting | Activity | Location / Area | Responsible (Sub) | Predecessor / Constraint | Status | Notes
This tab is a WEEKLY FEED you provide — paste/replace it each week rather than having Claude generate or recalculate it. Rolling 3-week window: drop week 1 as it completes and add a new week 3. Rows 2-5 are examples — delete before use.

## Photo Log
Photo Ref # | Date Taken | Area / Location | Description | Linked Daily Log Date | Linked RFI/CO/Risk # | File Name | Include in Next Owner Report?
Index of jobsite photos. Keep the actual image files in the same folder/Drive as this workbook, named to match File Name. Row 2 is an example — delete before use.

## Permit Tracker
| Project: | Norcross, GA | [11 empty] | Total Trades | 0 | Issued / In Hand | 0
| AHJ / Jurisdiction: | Gwinnett County, GA; Norcross, GA | [11 empty] | Action Needed | 0 | Expiring Soon | 0
Trade / Permit Type | Permit Required? | Responsible Party | Permit Number | Status | Application Date | Approval / Issue Date | Expiration Date | Notes / Next Action | Flag | Backup Documents | Backup Required? | Last Activity Date | Days Since Activity
Flag auto-computes: ACTION NEEDED if Required=Yes and not yet Applied, or if Rejected/Expired; EXPIRING SOON if In Hand and Expiration Date is within 30 days. Last Activity Date / Days Since Activity (blank once In Hand or Rejected) feed the Dashboard's Stale Items section. Row 6 is an example — delete before use. Research permit requirements for your jurisdiction and work scope with the Permit Skill before assuming this list is complete.

## Material Tracker
| Project: | Norcross, GA | [16 empty] | Total Materials | 0 | Overdue Deliveries | 0
| Job Number: | 15170000GR | [16 empty] | Not Ordered | 0 | Received | 0
Material # | Supplier / Vendor | Description | Responsible Person | Priority | Order Status | PO / Order # | Date Ordered | Expected Delivery | Date Received | Linked Submittal # | Notes / Next Action | Flag | Backup Documents | Backup Required? | Lead Time (days) | Vendor Contact | Last Activity Date | Days Since Activity
Flag auto-computes OVERDUE when Expected Delivery has passed with no Date Received and Status isn't Cancelled. Material # is a simple sequential ID for cross-referencing (e.g. from Submittal Log). Lead Time and Vendor Contact support the procurement responsibility matrix and cadence reports. Last Activity Date / Days Since Activity feed the Dashboard's Stale Items section. Row 6 is an example — delete before use.

## Drawing Log
| Project: | Norcross, GA
Drawing # | Drawing Description | Discipline | Rev 0 (Date — What Changed) | Rev 1 (Date — What Changed) | Rev 2 (Date — What Changed) | Rev 3 (Date — What Changed) | Rev 4 (Date — What Changed) | Rev 5 (Date — What Changed) | Current Rev # | Current Rev Date | Status | Backup Documents
Each Rev column holds that revision's date and a short note on what changed (added/removed/revised) — leave unused Rev columns blank. Use the Drawing Management Skill to do a full sheet-by-sheet comparison between two revisions when you have both PDFs; this log is the summary/index, not the comparison itself. Row 5 is an example — delete before use.

## Specification Log
| Project: | Norcross, GA
Spec Format / Edition:
Spec Section # | Section Title | Division | Classification System | Related Drawing(s) | Submittal Required? | Submittal Type | Closeout Requirement | Acceptable Products / Vendors | Linked RFI # | Linked Submittal # | Revision / Update Date | Status | Notes | Backup Documents
Spec Format / Edition (row 3) is set ONCE for the project — confirm it before logging sections; see the Specification Management Skill for how to identify it from the actual spec book's numbering pattern (MasterFormat 1995's 16 divisions vs. 2004+'s 50 divisions vs. UniFormat's element-based lettering are NOT interchangeable and section numbers mean different things in each). The per-row Classification System column is only for the rare case where one section doesn't match the project's stated format (e.g. an old base spec with a newer addendum section added in a different numbering). Use the Specification Management Skill to build the Submittal Register straight from this log (every row with Submittal Required? = Yes becomes a Submittal Log entry), and to register a new/updated section when the Owner issues a change. Row 6 is an example — delete before use.

## Owner Contract Key Terms
OWNER CONTRACT KEY TERMS
Extracted from the actual executed Owner Contract by the Owner Contract Skill. Values shown are common placeholders (mostly AIA A201 conventions, since that's the most widely used reference point) — NOT specific to your contract's actual form. GMP, Design-Build, IPD, ConsensusDocs, EJCDC, and custom Lump Sum contracts routinely set different terms entirely. CONFIRM every field against your actual executed contract, whatever form it takes, before relying on it.
Contract Form (AIA / GMP / DB / IPD / ConsensusDocs / EJCDC / Custom)
Retainage — Labor (%)
Retainage — Stored Materials (%)
Retainage Reduction Trigger
Payment Application Due Date
Payment Terms (days after application)
Change Order Notice / Pricing Deadline
Claim Notice Deadline (days)
Delay Notice Deadline (days)
Submittal Review Turnaround (days)
Closeout Submission Deadline (days before SC)
Closeout Requirements — Summary
Liquidated Damages ($/day)
Insurance Requirements — Summary
Dispute Resolution Method
Termination for Convenience Notice (days)
Last Reviewed / Extracted | 2026-10-01
Cells shaded light gray are for manual entry/extraction. This tab is a summary for quick reference only — the executed contract and its exhibits always govern; if this tab and the actual contract ever disagree, the contract wins.